| Project / Area |  | Date |  |
| --- | --- | --- | --- |
| Go Live scope |  | Cutover |  |

| Gate | Pass test | Evidence / link | Owner | Status |
| --- | --- | --- | --- | --- |
| Standardize & train ready | SOP frozen; visuals posted; all shifts trained & signed off | SOP ID/date; training record; photos of station visuals |  | ☐ Pass ☐ Hold |
| Data & master data loaded | Routings/cycle times/items/ labels loaded; test transactions completed; cutover plan signed | MD checklist; test log; signed cutover plan |  | ☐ Pass ☐ Hold |
| Controls & safety verified | E-stops/interlocks tested; hand-back to manual path proven; safe access/egress clear; alarms prioritized | Controls list; test record; safety sign-off |  | ☐ Pass ☐ Hold |
| Facilities & commissioning | Power/air/network commissioned; RF cover ok; guarding/clearances verified; manual fallback path ready | Commissioning sheet; RF spot checks; photos; fallback note |  | ☐ Pass ☐ Hold |
| Support & on-call in place | “03:00 on-site owner”; escalation chain posted; vendor SLA times confirmed; remote access tested/ approved | Contact list; SLA; remote access approval |  | ☐ Pass ☐ Hold |
| Spares & CMMS prepared | Critical spares kitted/labeled; CMMS PM tasks created; calibration plan defined | Spares list/locations; CMMS task IDs; calibration schedule |  | ☐ Pass ☐ Hold |
| Cyber & backups ready | Per-user accounts; least privilege set; configs backed up; rollback restore point available | Access list; backup log; restore test note |  | ☐ Pass ☐ Hold |

| Gate | Pass test | Evidence / link | Owner | Status |
| --- | --- | --- | --- | --- |
| Rollback plan tested | Documented steps; assets tagged; reversion ≤ 1 day; trial rollback executed or dry-run documented | Rollback plan; test log; asset map |  | ☐ Pass ☐ Hold |
| Validation & first article | First-article criteria defined; sample inspected; QA signs off; end-to-end traceability proven | FAI sheet; QA signature; traceability report |  | ☐ Pass ☐ Hold |
| Metrics & tracking live | Baseline captured; T51 set up; guardrails set; daily standup reviewing issues and numbers | T51 link; baseline sheet; standup cadence |  | ☐ Pass ☐ Hold |
| Communication & change control | Go-live brief delivered to all shifts; stop rule posted; version control & change approval set | Brief deck; notice photo; change log |  | ☐ Pass ☐ Hold |
| Compliance & documentation | CE/UL and risk file ready; permits completed; training records stored | Compliance pack; permit IDs; training log |  | ☐ Pass ☐ Hold |
| Handover & sustain plan | Ownership table complete; open-issues list live; 2-week and 8-week checks scheduled | Ownership list; issues log; calendar holds |  | ☐ Pass ☐ Hold |

- Stop rule (post go-live):

- Rollback notes:

How to use

Run this checklist in the go-live review (T-1 to T0) and again at the end of week 1.

If any gate = Hold:  fix the problem first, or, narrow pilot scope and time-limit it to mitigate.

How to use: Review the 5 gates before funding a pilot. If any fails, fix it first or keep the pilot very narrow and time-limited.

1) Process ready

What it means: There is one agreed “best way” to run the current process, and teams actually follow it.

Why it matters: Automation copies today’s method. If that varies by shift/person, you may not be locking in the best version.

How to check (quick)

- Watch the work on two shifts. Steps, order, and settings match the SOP.

- You have measured cycle time and changeover time in the last two weeks.

Evidence that passes: Current SOP ID and date; short time study sheet or line report; a note that all shifts use the same steps.

Common fixes if it fails: Walk the SOP with the team; align one method; add simple visual cues; re-measure for a week.

2) Data ready

What it means: All inputs that the pilot depends on are named, owned, and recent. Examples: item size and weight, label position, cycle times, defect codes.

Why it matters: If inputs are wrong or stale, the tool makes wrong decisions and trust drops fast.

How to check (quick)

- List the data the pilot needs. For each, name the source and the owner.

- Pull last month’s values and show where they came from.

Evidence that passes: One-page “data list” with source system or form, named owner, last refresh date, and an audit sample.

Common fixes if it fails: Assign owners; run a spot check on 20 items; correct obvious gaps; set a simple weekly refresh.

3) Safety and controls ready

What it means: Stop conditions, interlocks, checks, and safe access are defined. People know how to hand control back to a human if needed.

Why it matters: Safety and quality must work on day one. Missing controls often create delays or risk later.

How to check (quick)

- List the events that should stop the system and how it stops.

- Confirm how an operator safely enters the area, resets, and restarts.

Evidence that passes: Short “controls list” (stops, interlocks, checks), safe access notes, approver in Safety/QA/Maintenance.

Common fixes if it fails: Add guards or shrouds; define stop signals; write a reset procedure; agree who signs off changes.

4) Support ready

What it means: A named on-site person owns the system when it alarms, including nights and weekends. Spares and vendor help are in place.

Why it matters: Many pilots miss targets because stops take too long to fix.

How to check (quick)

- Name the on-site owner and the escalation chain.

- List the top five spares and where they are.

- Confirm vendor response times.

Evidence that passes: One-page contact list; spare parts list with locations; vendor SLA with response times; notes on remote access rules if used.

Common fixes if it fails: Train and assign an owner; stock critical spares; agree SLA terms; if this is not possible, choose simpler tech.

5) Economics ready

What it means: You know today’s cost and have modeled total cost of ownership (TCO) for the pilot and after. There is a plan to undo or redeploy the kit if the pilot misses.

Why it matters: Hidden costs and no fallback are common reasons ROI slips.

How to check (quick)

- Baseline: current labor time, scrap/rework, downtime, or travel minutes.

- TCO includes: equipment, integration hours, training time, software fees, install downtime, spares, vendor support, upgrades/obsolescence.

- Reversibility: where the kit goes if you stop.

Evidence that passes: One-page baseline and TCO summary; a sentence on the reversal or redeployment plan.

Common fixes if it fails: Complete the baseline with one week of measured data; add the missing cost items; define a clear redeploy target.