## HowToUse
Pilot Metrics Sheet
Purpose
Give an objective read on a pilot: primary metric vs. baseline (and optional comparator), plus safety/quality guardrails.
How to use
1) In Config, name the primary metric, target, direction (higher/lower is better), and the baseline & pilot date windows.
2) (Optional) Turn on the A/B comparator and log data rows tagged as ‘Comparator’ in the Data sheet.
3) In Data, log each measurement (daily or per shift). Add guardrail values if used, and any safety incidents.
4) See Metrics for baseline vs. pilot results, target check, guardrail breaches, and a simple decision helper.
Tips
- Control for demand swings by using consistent time buckets (e.g., daily) and note the volume column if relevant.
- Hit the target early? Decide whether to extend or move to scale. If not, stop cleanly or fix a specific cause.
- Use together with the Readiness Screener, the Stage-Gate checklist, and Pilot Charter.
Terminology
Guardrails
Guardrails = “do-no-harm” limits you watch during the pilot while you chase the primary win.
They’re there to prevent backsliding on safety, quality, or service.
You might push throughput up, but you mustn’t create safety incidents, spike defects, or kill service.
Typical guardrails:
Safety: incidents = 0 (binary Yes/No).
Quality: FPY ≥ target min; Defects per 1,000 ≤ max.
Service: OTIF ≥ min; WIP/lead time ≤ max.
Process limits: temp/pressure within ± band; alarm rate ≤ max/hour.
Baseline
The same line/process before the pilot, over a defined pre-pilot window (your “Baseline start/end” in Config). It answers: What was typical performance here before we changed anything?
Comparator
A parallel, unaffected line/station/shift during the pilot window (logged as Group = Comparator). It answers: What would performance look like at the same time without the pilot (so we control for noise like demand swings, mix, or upstream issues)?

## Config
Settings |  |  |  | Dropdown lists
Primary metric name | FPY (%) |  |  | YesNo | Yes
Primary direction | Higher is better |  |  |  | No
Primary target (number) | 95
Baseline start (date) | 2025-10-01 |  |  | Direction | Higher is better
Baseline end (date) | 2025-10-20 |  |  |  | Lower is better
Pilot start (date) | 2025-10-21
Pilot end (date) | 2025-10-29 |  |  | Group | Pilot
Use comparator (A/B) | Yes |  |  |  | Comparator
Min observations for decision | 20
|  |  |  | Shift | A
Guardrails (optional) |  |  |  |  | B
| Guardrail name | Direction | Threshold |  | C
G1 | Defects per 1000 | Lower is better | 10 |  | Day
G2 |  |  |  |  | Night
G3
Note: If you have a nominal target value, track a vriable like "distance to target" or "variance", with direction "Lower is better".

## Data
Date | Shift | Group | Volume | Primary metric | G1 value | G2 value | G3 value | Safety incident? | Notes
|  | Pilot / Comparator | units | value | Defects per 1000 |  |  | Yes / No
2025-10-13 | Night | Pilot | 50 | 95 | 12 |  |  | No
2025-10-13 | Night | Pilot | 50 | 94 | 10 |  |  | No
2025-10-13 | Night | Pilot | 50 | 93 | 10 |  |  | No
2025-10-13 | Night | Pilot | 50 | 95 | 11 |  |  | No
2025-10-13 | Night | Pilot | 50 | 96 | 9 |  |  | No
2025-10-13 | Night | Pilot | 50 | 94 | 12 |  |  | Yes
2025-10-13 | Night | Pilot | 50 | 97 | 8 |  |  | No
2025-10-13 | Night | Pilot | 50 | 92 | 10 |  |  | No
2025-10-13 | Day | Pilot | 50 | 98 | 10 |  |  | No
2025-10-28 | Night | Comparator | 50 | 94 | 10 |  |  | No
2025-10-28 | Night | Pilot | 50 | 93 | 10 |  |  | Yes
2025-10-28 | Night | Pilot | 50 | 95 | 11 |  |  | No
2025-10-28 | Night | Comparator | 50 | 96 | 9 |  |  | No
2025-10-28 | Night | Pilot | 50 | 94 | 12 |  |  | No
2025-10-28 | Night | Pilot | 50 | 97 | 8 |  |  | No
2025-10-28 | Night | Pilot | 50 | 92 | 10 |  |  | No
2025-10-28 | Day | Comparator | 50 | 98 | 10 |  |  | No
2025-10-28 | Night | Pilot | 50 | 94 | 10 |  |  | No
2025-10-28 | Night | Pilot | 50 | 93 | 10 |  |  | No
2025-10-28 | Night | Pilot | 50 | 95 | 11 |  |  | No
2025-10-28 | Night | Comparator | 50 | 96 | 9 |  |  | No
2025-10-28 | Night | Pilot | 50 | 94 | 12 |  |  | No
2025-10-28 | Night | Pilot | 50 | 97 | 8 |  |  | No
2025-10-28 | Night | Pilot | 50 | 92 | 10 |  |  | No
2025-10-28 | Day | Pilot | 50 | 98 | 10 |  |  | No
2025-10-28

## Metrics
Pilot Metrics - Results
Primary metric | FPY (%) |  | As-of date | 2025-10-24
Target | 95 |  | Enough observations? | No
Direction | Higher is better |  | Meets target? | No
Period
| Start date | End date
Baseline | 2025-10-01 | 2025-10-20
Pilot | 2025-10-21 | 2025-10-29
Pilot window |  |  | Baseline window
Pilot N | 12 |  | Baseline N | 9
Pilot mean | 94.5 |  | Baseline mean | 94.8889
Δ vs baseline | -0.38889
Guardrails (breaches in pilot window) |  |  | Comparator
Defects per 1000 | 2 |  | Comparator used? | Yes
| 0 |  | Comparator N (pilot window) | 4
| 0 |  | Comparator mean | 96
|  |  | Pilot Δ vs Comparator | -1.5
Safety incidents (pilot window)
Count | 1