This pack contains three sections to plan and run Business Continuity drills and capture results:

- Drill Scenario

- Action Log

- Test Log

Use it for tabletop walk-throughs or live simulations.

Overall approach (keep it practical)

- Protect people first: EHS controls, pause authority, and safe test conditions are non-negotiable.

- Prove flow: can you stop safely, contain the issue, re-route work, and restart within acceptable limits?

- Stress what matters: choose scenarios that challenge order fulfillment, safety, quality, or cold-chain integrity.

- Define “good” ahead of time: who decides, by when, with what evidence (e.g., restart times, temp logs, truck departures).

- Capture facts: times, quantities, backlog, scrap, and who did what. Stories are useful; numbers change behavior.

- Close the loop the same day: assign owners, raise work orders/tickets, update the BCP and SOPs.

Prepare (60–90 minutes, max)

- Pick scenario & objective in one line each (e.g., “Partial power loss in Filling Hall; sustain 60% output within 2 hours”).

- Define scope & constraints: areas, assets, shifts, no real damage or chemicals, no live fire/water release, etc.

- Assign roles: coordinator, timekeeper, scribe, area owner(s), maintenance, quality, EHS, logistics/transport, customer service.

- Draft 5–10 injects (events) that force decisions (e.g., “compressor fails; chilled water at risk in 30 min”).

- Set success criteria: restart times, minimum throughput, max scrap, max temperature excursion, customer comms time.

- Print: Action Log (several copies), participant list, injects timeline; bring radios/phones.

- Brief (5 min): objective, safety rules, where we’ll walk, what we simulate vs. just discuss.

Tip: Print the Action Log for the drill. Use pen on the floor; transcribe to the file after.

Scenario design

Scenarios ideas:

- Specific utility loss with business impact (e.g., power outage in one hall, compressed air failure, steam off).

- Transport strike or bridge closure: can we ship critical orders via alternates within 24h?

- Flooded access road: how do inbound RM and outbound FG flow?

- Fire in warehouse aisle (simulated): evacuation, cordon, inventory impact, re-slot plan.

- Chiller/HVAC failure: cold chain at risk; product hold/disposition decisions.

- Forklift incident blocks main aisle: material flow reroute, safety, alternate pick paths.

- Supplier miss/quality hold: switch to alternate material or re-sequence schedule.

- Regulatory stop on Line 2: capacity reallocation to meet customer SLA.

- OT/SCADA breakdown: manual workarounds and data capture.

- Server failure / Cyber attack: typical IT Recovery Plan drill.

Avoid:

- Vague scenarios: “Everything goes wrong.”

- Purely technical scenarios with no flow or customer impact.

- Hero plans without constraints (“we’ll just do overtime”) and no evidence.

- Scope creep

- Changing rules mid-run

- Simulating hazards unsafely

During the drill

- Coordinator runs injects; timekeeper calls times; scribe logs in the Action Log.

- Use hh:mm; record stop/start times, throughput estimates, scrap, queue lengths, truck ETDs/ATDs.

- If an inject is unclear, pause, agree the assumption, then continue.

- Note evidence: photos, batch/route card timestamps, SCADA trend screenshot, temp log, weighbridge ticket, carrier confirmation.

After the drill (same day)

- Complete the Test Log for each critical process/system: test step, Result (Pass/Fail), evidence link, issues, owner, retest date.

- Decide next actions and log them as real work:

  - Fixes: spare parts, valve labeling, alternate pick paths, generator test procedure, cross-dock plan, comms templates.

  - BCP updates: Priority List (what first), Fallbacks (alternate lines/routes/suppliers) with entry/exit criteria, At-Risk Board items.

  - SOP/Work instruction updates: emergency stop-start, manual picks, temp checks, hold/release workflow.

  - Training: quick refreshers for teams involved.

  - Next drill: scope, owner, target date.

Make it effective: Open maintenance work orders and CI tickets now.

Incorporate learnings into the BCP

- Priority List: confirm realistic restart order and target rates by area/line; where needed, adjust owners.

- Fallbacks: add tested alternates (e.g., Line 3 can run SKU X at 70% with changeover < 45 min).

- At-Risk Board: items that failed or lack evidence stay visible until closed.

- Materials & suppliers: list alternatives, MOQ/lead-time, pre-approved substitutions.

- Transport: pre-cleared carriers, alternative lanes, cross-dock sites, night-shift pickup windows.

- Buffers: review safety stock and WIP buffers for top SKUs.

- Versioning:  Update BCP version/date and email the change note to stakeholders.

Common pitfalls

- No EHS lead present → unsafe shortcuts or delays.

- No authority to stop/restart → confusion and finger-pointing.

- Utilities assumed, not measured → generator/compressor/chiller capacity unverified.

- Tight chokepoints (one aisle, one dock) with no reroute plan.

- Relying on a single expert → drill collapses when that person is unavailable.

- Fixes agreed but no work orders/tickets → nothing changes.

Checklist

Pre-drill

 Scenario & objective agreed   Scope/assumptions safe   Roles assigned (incl. EHS, QA, Maint, Logistics)   Injects timeline ready   Success criteria defined (throughput, restart, temp, ETD)   Action Log printed

During

 Exact times logged   Flow, backlog, scrap captured   Evidence noted   Pauses used to clarify

Post-drill

 Test Log completed   Fix tickets/work orders raised   BCP/SOPs updated & versioned
 Next drill scheduled   Summary sent to ops + customer service + site leadership

What’s in this file

- Drill Scenario — overview, objectives, scope/constraints, participants, injects.

- Action Log — timestamps, actions/decisions, outcomes, issues, follow-ups, status.

- Test Log — per process/system: test step, result, evidence, owner, retest date.

Opionally, start with a short ‘tabletop’ on the floor. Prove safe stop, reroute, and restart. Then add realism in the next drill.

Scenario overview

| Scenario name | Date | Coordinator | Location(s) |
| --- | --- | --- | --- |
| Objectives (top 3) |  |  |  |
| In-scope processes / systems |  | Out of scope (explicit) |  |
| Assumptions |  | Constraints / Rules of engagement |  |

Participants & roles

| Name | Role | Org/Team | Phone | Email |
| --- | --- | --- | --- | --- |

Injects timeline (for tabletop/drill)

| Time (hh:mm) | Inject / Event | Expected actions | Observation notes |
| --- | --- | --- | --- |

| Timestamp (hh:mm) | Actor / Team | Action / Decision | Expected outcome | Actual outcome / Evidence | Issue? (Y/N) | Follow-up / Owner | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |

| Critical process / system | RPO* | RTO* | Test step | Result (Pass/Fail) | Evidence (link/ref) | Issues found | Owner | Retest date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

*	RPO (Recovery Point Objective):  Maximum tolerable data loss, measured in time.

The “how far back” you must be able to restore data. E.g., RPO = 4h: you can lose at most 4 hours of transactions.

RTO (Recovery Time Objective):  Maximum tolerable outage duration for a process/system.

The “how fast” you must restore service. E.g., RTO = 8h → the process must be up again within 8 hours.