## HowToUse
BCP Starter Pack
What this pack includes
• BCP Priority List
• Fallback Matrix
• Print-friendly Dashboards
How to use (fast path)
1) In Priority_List, enter one row per critical process/service.
– You can use the Risk Register / Priority Board tool as your source
– Keep IDs simple (e.g., BCP-01, BCP-02).
– Set RTO (hours) and, if relevant, RPO (hours).
– Choose Owner and Priority (High/Medium/Low).
2) In Fallbacks, add one or more fallback options for each BCP-XX.
– Triggers • short steps • Limit (hours) • roles • prereqs • revert steps.
3) See Dashboards for print-ready views (Priority Board, Fallback Cards).
Notes & tips
• This pack combines multiple tools for convenience and traceability.
• You can leave Config defaults as-is; adjust lists later if helpful.
• A few lines of sample data have been included for illustration
Glossary:
RPO (Recovery Point Objective)
Maximum tolerable data loss, measured in time. The “how far back” you must be able to restore data. Example: RPO = 4h → you can lose at most 4 hours of transactions.
RTO (Recovery Time Objective)
Maximum tolerable outage duration for a process/system. The “how fast” you must restore service. Example: RTO = 8h → the process must be up again within 8 hours.

## Config
Priority_levels | Owners | Roles
High | Ops Lead | Operator
Medium | IT | Team Lead
Low | QA | Maintenance
| HR | IT
| Logistics | QA
| Safety | Security
| Maintenance | Warehoiuse
Planner

## Priority_List
BCP – Priority Risks
Risk ID (from Register) | BCP Item ID | Critical process/service | Impact if down | RTO (hours) | RPO (hours) | Owner | Priority | Dependencies (systems/suppliers) | Runbook section link | Notes | Has fallback? | Any fallback meets RTO? | helper:Issue | helper:PriRank | Helper:RankKey
1003 | BCP-01 | WMS order release | Shipments cannot be waved; picks stop | 4 | 1 | IT | High | ERP; Network; Label printers | SRR §2.1 | Swap to paper wave list if needed | Yes | Yes | OK | 3
1011 | BCP-02 | Traceability database | Cannot ship; compliance risk | 8 | 2 | QA | Low | ERP; DB server; Backups | SRR §2.2 | Manual lot logs as interim | Yes | No | RTO unmet | 1 | 199991
1006 | BCP-03 | Picking station operation | No picks at primary area | 8 | 0 | Ops Lead | High | WMS; RF scanners; Wi-Fi | SRR §3.1 | Move orders to aisle B if needed | Yes | Yes | OK | 3
1014 | BCP-04 | Site Wi-Fi for RF/AMR | RF guns offline; AMRs stall | 4 | 0 | IT | Medium | Controllers; Switches; UPS | SRR §3.2 | Use tethered scanners as fallback | Yes | Yes | OK | 2
1023 | BCP-05 | Packing / labeling cell | Packs can’t be closed or labeled | 12 | 0 | Ops Lead | High | WMS; Labelers; Scales | SRR §3.3 | Preprint emergency labels | No |  | No fallback | 3 | 399987
1022 | BCP-06 | PLC / controls network | Machines can’t be started/reset | 4 | 0 | Maintenance | High | Switches; Firewall; VLANs | SRR §4.1 | Local manual mode where safe | Yes | Yes | OK | 3
1009 | BCP-07 | Endpoint AV management | HMIs quarantined; access blocked | 24 | 0 | IT | Medium | AV server; Policy repo | SRR §4.2 | Whitelist HMIs; freeze policy | No |  | No fallback | 2 | 299975
1016 | BCP-08 | Machine guarding checks | Area locked until safe verification | 2 | 0 | Ops Lead | Medium | Training; Checklists | SRR §5.1 | Use alternate station if open | No |  | No fallback | 2 | 299997
1012 | BCP-09 | AMR fleet control | No internal moves; kitting delays | 12 | 0 | Logistics | High | Wi-Fi; Fleet server | SRR §5.2 | Manual tugger route plan | Yes | Yes | OK | 3
1018 | BCP-10 | Forklift availability | Loading/putaway backlog | 6 | 0 | Logistics | Medium | Keys; Chargers; Spare unit | SRR §5.3 | Prioritize docks; rent spare | No |  | No fallback | 2 | 299993
1020 | BCP-11 | Recipe governance | Mis-set parameters risk quality | 8 | 0 | Ops Lead | Medium | MES; QA sign-off | SRR §6.1 | Use last approved recipe pack | Yes | Yes | OK | 2
1017 | BCP-12 | Vendor ASN portal | Blind receipts; dock congestion | 24 | 8 | Planner | Low | Internet; ERP EDI | SRR §6.2 | Receive to quarantine; paper ASN | Yes | Yes | OK | 1

## Fallbacks
BCP – Fallback options
BCP Item ID | Fallback option (what you switch to) | Trigger (when) | Steps (very short) | Limit (hours) | Roles needed | Prereqs (spares/access) | Revert steps | Owner
BCP-01 | Paper wave lists | WMS unavailable >5 min | Print wave list; assign; confirm picks later | 8 | Team Lead; Warehouse | Printer; last export | Import catch-up; close paper orders | IT
BCP-02 | Manual lot log & hold | Traceability DB down | Record lot on form; hold; QA sign | 4 | QA; Operator | Forms; hold area | Back-enter lots; release holds | QA
BCP-03 | Move to Aisle B | Primary station down | Redirect picks; brief team; update board | 24 | Team Lead | Spare totes; labels | Move back; clear temp labels | Ops Lead
BCP-04 | Tethered scanners | Site Wi-Fi outage | Plug USB scanners; switch client mode | 6 | IT; Operator | USB scanners; cables | Switch back to RF; test roaming | IT
BCP-06 | Local manual mode | Controls network down | Switch PLC local; safe speed; manual resets | 4 | Maintenance; Ops Lead | SOP; keys | Return to network; verify interlocks | Maintenance
BCP-09 | Manual tugger route | AMR fleet offline | Start hourly tug loop; post stops; log pickups | 16 | Logistics | Tugger; driver | Resume AMRs; close logs | Logistics
BCP-11 | Last approved recipe pack | Recipe server unavailable | Use printed recipe; double-check set-points | 12 | Ops Lead; QA | Printed pack; sign-off | Load latest recipe; archive paper | Ops Lead
BCP-12 | Paper ASN + quarantine | Vendor portal down | Receive to quarantine; paper ASN; later match | 48 | Planner; QA | Forms; quarantine location | Back-match; move to stock | Planner

## At-Risk Dashboard
BCP – At-Risk items
BCP Summary KPIs
Total BCP items | 12 |  | % items with ≥1 fallback |  | 66.67%
Without fallback | 4 |  | % items with fallback meeting RTO |  | 58.33%
At Risk Board
BCP Item ID | Critical process/service | RTO (h) | Owner | Priority | Issue
BCP-05 | Packing / labeling cell | 12 | Ops Lead | High | No fallback
BCP-08 | Machine guarding checks | 2 | Ops Lead | Medium | No fallback
BCP-10 | Forklift availability | 6 | Logistics | Medium | No fallback
BCP-07 | Endpoint AV management | 24 | IT | Medium | No fallback
BCP-02 | Traceability database | 8 | QA | Low | RTO unmet

## Fallbacks Overview
BCP Fallbacks overview
BCP Item ID | Fallback option | Trigger | Steps | Limit (h) | Roles | Prereqs | Revert steps | Owner
BCP-01 | Paper wave lists | WMS unavailable >5 min | Print wave list; assign; confirm picks later | 8 | Team Lead; Warehouse | Printer; last export | Import catch-up; close paper orders | IT
BCP-02 | Manual lot log & hold | Traceability DB down | Record lot on form; hold; QA sign | 4 | QA; Operator | Forms; hold area | Back-enter lots; release holds | QA
BCP-03 | Move to Aisle B | Primary station down | Redirect picks; brief team; update board | 24 | Team Lead | Spare totes; labels | Move back; clear temp labels | Ops Lead
BCP-04 | Tethered scanners | Site Wi-Fi outage | Plug USB scanners; switch client mode | 6 | IT; Operator | USB scanners; cables | Switch back to RF; test roaming | IT
BCP-06 | Local manual mode | Controls network down | Switch PLC local; safe speed; manual resets | 4 | Maintenance; Ops Lead | SOP; keys | Return to network; verify interlocks | Maintenance
BCP-09 | Manual tugger route | AMR fleet offline | Start hourly tug loop; post stops; log pickups | 16 | Logistics | Tugger; driver | Resume AMRs; close logs | Logistics
BCP-11 | Last approved recipe pack | Recipe server unavailable | Use printed recipe; double-check set-points | 12 | Ops Lead; QA | Printed pack; sign-off | Load latest recipe; archive paper | Ops Lead
BCP-12 | Paper ASN + quarantine | Vendor portal down | Receive to quarantine; paper ASN; later match | 48 | Planner; QA | Forms; quarantine location | Back-match; move to stock | Planner