## HowToUse
Risk Register Pack
Purpose
Keep one source of truth for risks.
Drive action via linked views (Heatmap, OPI Panel, Priority Board).
What's included
1- Risk Register (Cause → Event → Consequence; scoring; RAG; reviews)
2- Heatmap (5×5 L×I counts from Register)
3- OPI Panel (process KPIs: Risks, actions and responsiveness
4- Priority Board (print-ready top-20 risks by score)
How to use (quick)
1) Set thresholds & owners in Config (or keep defaults).
2) Log risks in Register
3) Print Heatmap and Priority Board for reviews; use OPI Panel monthly.

## Config
Settings
Priority thresholds (L×I)
High min | 15
Medium min | 8
Dropdown lists
Status |  | Treatment | Category | Owner
Open |  | Avoid | Safety | — add names —
Mitigate |  | Reduce | Quality
Monitor |  | Transfer | Delivery
Closed |  | Accept | Cost
People
Compliance
RAG |  |  | Cyber
Red |  |  | Supply
Amber
Green

## Register
Risk ID | Title / Description | Category | Scope/Site | Owner | Date raised | Cause | Event | Consequence | Impact (1-5) | Likelihood (1-5) | Score (=I*L) | Suggested priority (auto) | Priority (manual override) | Priority (used) | Treatment | Amber trigger (prepare) | Red trigger (act) | Current mitigation | Mitigation funded? | Status | Red / Amber / Green | Next action | Due date | Residual accepted by | Review date | Last review date | Date closed | Amber fired date | First action date | Red fired date | Restore date | Notes
1001 | Ergo strain at pick station | Safety | Warehouse | Ops Lead | 2025-09-15 | Awkward reach heights | Frequent micro-pauses | Operator injury risk | 4 | 4 | 16 | High |  | High | Avoid |  |  | Reduce shelf height | Y | Closed | Green | Check new shelf height. |  |  | 2025-11-04 | 2025-10-20 | 0 |  |  | 2025-10-02 | 2025-10-05
1002 | Mislabeled lots | Quality | Packaging | QA Lead | 2025-08-30 | Label template confusion | Wrong label applied | Recall exposure | 5 | 2 | 10 | Medium |  | Medium | Avoid |  |  |  | Y | Mitigate | Amber | Install backup | 2025-10-20 |  | 2025-11-06 | 2025-10-18 |  | 2025-10-18 | 2025-10-25
1003 | Shuttle downtime | Delivery | AS/RS | Maintenance | 2025-09-28 | Drive wheel wear | Unexpected stop | Orders delayed | 4 | 4 | 16 | High |  | High | Reduce |  |  | Replace AS/RS drive wheel | Y | Open | Green | Confirm parts order | 2025-11-20 |  | 2025-10-27 | 2025-10-23 |  |  |  | 2025-10-18 | 2025-10-25
1004 | Compressor trip | Cost | Utilities | Maintenance | 2025-09-10 | Differential pressure spike | Trip & restart | Energy waste | 3 | 2 | 6 | Low |  | Low | Avoid |  |  |  | Y | Monitor | Green |  |  |  | 2025-11-06 | 2025-10-10
1005 | High changeover scrap | Quality | Line A | Ops Lead | 2025-09-05 | Imprecise fixture | First-off defects | Scrap spike | 3 | 3 | 9 | Medium |  | Medium | Avoid |  |  |  | Y | Open | Amber |  |  |  | 2025-11-08 | 2025-10-21
1006 | Pallet jams at merge | Delivery | Warehouse | Logistics | 2025-09-22 | Photoeye misalign | Backups on conveyor | Dock queue | 4 | 3 | 12 | Medium |  | Medium | Reduce |  |  |  | Y | Mitigate | Amber |  |  |  | 2025-10-27 | 2025-10-17
1007 | Hard stop bypass | Safety | Line B | Ops Lead | 2025-09-12 | Bypassed interlock | Unsafe restart | Potential injury | 5 | 2 | 10 | Medium |  | Medium | Avoid |  |  |  | Y | Open | Red |  |  |  | 2025-10-27 | 2025-10-22
1008 | Overtime burnout | People | Assembly | Ops Lead | 2025-08-25 | Chronic OT | Absenteeism rises | Throughput slip | 4 | 2 | 8 | Medium | High | High | Avoid |  |  |  | N | Monitor | Amber |  |  |  | 2025-10-29 | 2025-10-19
1009 | Outdated AV signatures | Cyber | IT Systems | IT | 2025-09-29 | Lagging updates | Malware exposure | System downtime | 3 | 3 | 9 | Medium |  | Medium | Avoid |  |  |  | Y | Closed | Amber |  |  |  | 2025-10-30 | 2025-10-24
1010 | ASN errors from vendor | Supply | Inbound EDI | Planner | 2025-09-07 | Mapping drift | Mismatched receipts | Stockouts | 4 | 2 | 8 | Medium |  | Medium | Reduce |  |  |  | Y | Mitigate | Amber |  |  |  | 2025-11-02 | 2025-10-15
1011 | Traceability gaps | Compliance | Packaging | QA Lead | 2025-09-18 | Missing scan step | Lot not linked | Regulatory breach | 5 | 2 | 10 | Medium |  | Medium | Avoid |  |  | Add forced scan at labeler | n/a | Open | Green |  |  |  | 2025-10-29 | 2025-10-22 |  | 2025-10-02 | 2025-10-25
1012 | AMR battery failures | Delivery | Warehouse | Logistics | 2025-10-01 | Bad charging discipline | Mid-shift drop | Fulfillment delays | 4 | 3 | 12 | Medium |  | Medium | Avoid |  |  |  | Y | Open | Amber |  |  |  | 2025-11-08 | 2025-10-24
1013 | Tooling wear not tracked | Quality | Line A | Maintenance | 2025-09-03 | No usage counter | Dimensional drift | Customer complaints | 3 | 3 | 9 | Medium |  | Medium | Avoid |  |  |  | Y | Monitor | Amber |  |  |  | 2025-11-09 | 2025-10-16
1014 | Wi-Fi dead zones | Data | IT Systems | IT | 2025-08-22 | AP coverage gaps | Dropped terminals | Picking stops | 4 | 2 | 8 | Medium |  | Medium | Avoid |  |  |  | Y | Mitigate | Green |  |  |  | 2025-11-08 | 2025-10-14
1015 | Spare parts lead time | Supply | Maintenance | Maintenance | 2025-09-26 | Sole supplier | Long outage risk | MTTR misses | 2 | 4 | 8 | Medium |  | Medium | Reduce |  |  |  | Y | Open | Amber |  |  |  | 2025-11-08 | 2025-10-23
1016 | Guarding left open | Safety | Line B | Ops Lead | 2025-10-05 | Incomplete reset | Access while running | Harm risk | 5 | 2 | 10 | Medium |  | Medium | Avoid |  |  | Add interlock reset checklist | n/a | Open | Amber | Assign checklist | 2025-11-12 |  | 2025-11-03 | 2025-10-24 |  |  |  | 2025-10-18 | 2025-10-25
1017 | Incorrect BOM in ERP | Quality | Planning | Planner | 2025-09-09 | Data entry error | Wrong picks | Build errors | 4 | 2 | 8 | Medium |  | Medium | Avoid |  |  |  | Y | Mitigate | Amber |  |  |  | 2025-10-27 | 2025-10-20
1018 | Forklift near-misses | Safety | Warehouse | Logistics | 2025-09-21 | Crowded aisles | Near collisions | Injury risk | 4 | 3 | 12 | Medium |  | Medium | Avoid |  |  | Mark forklift lanes | n/a | Open | Amber | Order materials | 2025-11-02 |  | 2025-10-30 | 2025-10-23
1019 | Expired calibration | Quality | Lab | QA Lead | 2025-09-30 | Overdue gages | Bad measurements | False accept | 2 | 2 | 4 | Low |  | Low | Avoid |  |  | Calibrate high-risk gages | n/a | Open | Amber | Assign task | 2025-11-01 |  | 2025-11-09 | 2025-10-24
1020 | Recipe overrides | Compliance | Process | Ops Lead | 2025-09-11 | Operator bypass Deviation | Non-conform run | Rework | 3 | 3 | 9 | Medium |  | Medium | Avoid |  |  |  | Y | Monitor | Amber |  |  |  | 2025-11-03 | 2025-10-18
1021 | Spoilage in cold room | Cost | Warehouse | Logistics | 2025-09-16 | Door left ajar | Temp excursions | Write-offs | 4 | 2 | 8 | Medium | Low | Low | Avoid |  |  |  | Y | Mitigate | Amber |  |  |  | 2025-10-28 | 2025-10-21
1022 | Unpatched PLCs | Cyber | Process | IT | 2025-10-02 | Missed firmware | CVE exposure | Unexpected halt | 3 | 3 | 9 | Medium |  | Medium | Avoid |  |  |  | N | Open | Red |  |  |  | 2025-11-02 | 2025-10-24
1023 | Critical mold crack | Quality | Line B | Maintenance | 2025-10-06 | Fatigue crack | Surface defects | Customer returns | 4 | 4 | 16 | High |  | High | Avoid |  |  | Tooling repair order | N | Open | Red |  |  |  | 2025-10-29 | 2025-10-24
1024 | Vendor capacity risk | Supply | External | Planner | 2025-09-08 | Single-source vendor | Lead-time spike | Backorders | 4 | 3 | 12 | Medium |  | Medium | Reduce |  |  |  | N | Monitor | Red |  |  |  | 2025-11-04 | 2025-10-17
1025 | AM cleaning skipped | People | Line A | Ops Lead | 2025-09-19 | Poor AM adherence | Debris buildup | Stops/quality loss | 3 | 3 | 9 | Medium |  | Medium | Avoid |  |  |  | N | Mitigate | Red |  |  |  | 2025-11-01 | 2025-10-22
Transfer
Formulas:
Date closed = [First action date]

## Heatmap
Impact x Likelihood Heatmap
| 5 | 0 | 4 | 0 | 0 | 0
| 4 | 0 | 5 | 4 | 3 | 0
Impact | 3 | 0 | 1 | 6 | 0 | 0
| 2 | 0 | 1 | 0 | 1 | 0
| 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 2 | 3 | 4 | 5
Likelihood

## OPIs
Risk Register - OPIs
Open risks | 23 | As-of date | 2025-10-27
Prriority High | 2
Prriority Medium | 19
Prriority Low | 2 | Actions
|  | % High & Medium priority risks funded | 73.68%
Responsiveness |  | Open actions | 5
Average Time amber → first action (days) | 15 | Actions overdue | 1
Average Time red → restore (days) | 5.6667

## Priority Risk board
Risk Register - Top 20 | [10 empty] | Top | 20
[11 empty] | Helper key | Helper key | Helper key
Rank | Risk ID | Title / Description | Category | Owner | Priority | Score | Next review | Status | RAG | Next action | rank score/row | desc
1 | 1023 | Critical mold crack | Quality | Maintenance | High | 16 | 2025-10-29 | Open | Red | 0 |  | 3016024 | 24
2 | 1003 | Shuttle downtime | Delivery | Maintenance | High | 16 | 2025-10-27 | Open | Green | Confirm parts order | 2010003 | 3016004 | 4
3 | 1008 | Overtime burnout | People | Ops Lead | High | 8 | 2025-10-29 | Monitor | Amber | 0 | 3016004 | 3008009 | 9
4 | 1024 | Vendor capacity risk | Supply | Planner | Medium | 12 | 2025-11-04 | Monitor | Red | 0 | 1006005 | 2012025 | 25
5 | 1018 | Forklift near-misses | Safety | Logistics | Medium | 12 | 2025-10-30 | Open | Amber | Order materials | 2009006 | 2012019 | 19
6 | 1012 | AMR battery failures | Delivery | Logistics | Medium | 12 | 2025-11-08 | Open | Amber | 0 | 2012007 | 2012013 | 13
7 | 1006 | Pallet jams at merge | Delivery | Logistics | Medium | 12 | 2025-10-27 | Mitigate | Amber | 0 | 2010008 | 2012007 | 7
8 | 1016 | Guarding left open | Safety | Ops Lead | Medium | 10 | 2025-11-03 | Open | Amber | Assign checklist | 3008009 | 2010017 | 17
9 | 1011 | Traceability gaps | Compliance | QA Lead | Medium | 10 | 2025-10-29 | Open | Green | 0 |  | 2010012 | 12
10 | 1007 | Hard stop bypass | Safety | Ops Lead | Medium | 10 | 2025-10-27 | Open | Red | 0 | 2008011 | 2010008 | 8
11 | 1002 | Mislabeled lots | Quality | QA Lead | Medium | 10 | 2025-11-06 | Mitigate | Amber | Install backup | 2010012 | 2010003 | 3
12 | 1025 | AM cleaning skipped | People | Ops Lead | Medium | 9 | 2025-11-01 | Mitigate | Red | 0 | 2012013 | 2009026 | 26
13 | 1022 | Unpatched PLCs | Cyber | IT | Medium | 9 | 2025-11-02 | Open | Red | 0 | 2009014 | 2009023 | 23
14 | 1020 | Recipe overrides | Compliance | Ops Lead | Medium | 9 | 2025-11-03 | Monitor | Amber | 0 | 2008015 | 2009021 | 21
15 | 1013 | Tooling wear not tracked | Quality | Maintenance | Medium | 9 | 2025-11-09 | Monitor | Amber | 0 | 2008016 | 2009014 | 14
16 | 1005 | High changeover scrap | Quality | Ops Lead | Medium | 9 | 2025-11-08 | Open | Amber | 0 | 2010017 | 2009006 | 6
17 | 1017 | Incorrect BOM in ERP | Quality | Planner | Medium | 8 | 2025-10-27 | Mitigate | Amber | 0 | 2008018 | 2008018 | 18
18 | 1015 | Spare parts lead time | Supply | Maintenance | Medium | 8 | 2025-11-08 | Open | Amber | 0 | 2012019 | 2008016 | 16
19 | 1014 | Wi-Fi dead zones | Data | IT | Medium | 8 | 2025-11-08 | Mitigate | Green | 0 | 1004020 | 2008015 | 15
20 | 1010 | ASN errors from vendor | Supply | Planner | Medium | 8 | 2025-11-02 | Mitigate | Amber | 0 | 2009021 | 2008011 | 11
1008022
2009023
3016024
2012025
2009026
Formulas:
Next review = IF([Helper key]="","", INDEX(Register!$Z:$Z, [Helper key]))